## Sheet1
Major Tasks | Subtasks - Critical Floating | Duration(in 1/2 week segments) | % of Completion | March Week 1 | March Week 2 | March Week 3 (Spring Break) | March Week 4 | April Week 1 | April Week 2 | April Week 3 | April Week 4 | Post-Semester?
Design Phase 1 |  | 2 | 0
| UI Framework | 2 | 0
| Object diagrams | 2 | 0
Independent Phase 2 |  | 5 | 0
| Make classes (board, pieces, etc.) | 3 | 0
| Backend code for scripting | 5 | 0
| backend code for board/pieces | 5 | 0
| Board selection and general game creation screens | 5 | 0
Merging Phase 3 |  | 3 | 0
| Make the scripting UI functional (connect UI with functions) | 3 | 0
| Attach scripting to pieces and tiles | 2 | 0
| Finish adding functionality to UI | 3 | 0
Gameplay Phase 4 |  | 3 | 0
| Displaying board, pieces, etc into gameplay | 2 | 0
| Adding interactivity to pieces and other UI | 3 | 0
| Turn progression | 2 | 0
Testing Phase 5 |  | 2 | 0
| Testing | 2 | 0
0
Make Document of Features we want to add |  | 4 | 0
Design Sprites for Pieces |  | 3 | 0
Save Codes |  | 1 | 0
backend gameplay-specific piece/board interactions not done previously |  | 3 | 0