## Sheet1
i | Subtasks - Critical Floating | Duration(in 1/2 week segments) | % of Completion | March Week 1 | March Week 2 | March Week 3 (Spring Break) | March Week 4 | April Week 1 | April Week 2 |  | April Week 3 | April Week 4 |  | Post-Semester?
Design Phase 1 |  | 2 | 100
| UI Framework | 2 | 100
| Object diagrams | 2 | 100
Independent Phase 2 |  | 7 | 100
| Make classes (board, pieces, etc.) | 3 | 100
| Backend code for scripting | 5 | 100
| backend code for board/pieces | 5 | 100
| Start the HTML for game creation screens | 5 | 100
Merging Phase 3 |  | 3 | 100
| Make the scripting UI functional (connect UI with functions) | 3 | 100
| Attach scripting to pieces and tiles | 2 | 100
| Connect UI screens together | 3 | 100
Gameplay Phase 4 |  | 3 | 0
| Displaying board, pieces, etc into gameplay | 2 | 0
| Adding interactivity to pieces and other UI | 3 | 0
| Turn progression | 2 | 50
Testing Phase 5 |  | 2 | 0
| Testing | 2 | 0
0
Make Document of Features we want to add |  | 4 | 100
Design Sprites for Pieces |  | 3 | 100
Save Codes |  | 1 | 50
backend gameplay-specific piece/board interactions not done previously |  | 3 | 0
Present
Single question marks in completion % are estimates, multiple question marks in completion are because at least one group member did not attend our most recent meeting where the GANTT chart was updated, pure question marks are because we don't know how big the task is
[11 empty] | RAPS |  | Demo